## Sheet1
MaaS Customization
ID | Work Item | Task Description | PM (Man-Days) | Architect (Man-Days) | Software Developer (Man-Days) | QA Engineer (Man-Days) | Remarks
1 | UI/UX Style Customization |  | 3 | 3 | 9 | 2
1.1 | Design Specification Analysis & Alignment | Analyze SCCC platform's design guidelines (logo, color palette, fonts, icons, etc.). Reverse-engineer specifications if not provided. | 3 |  |  |  | PM handles client communication; Architect participates in technical review.
1.2 | Global Theme & Color Scheme Replacement | Establish a theme system in the MaaS frontend codebase to match SCCC's style and apply it globally. |  | 3 | 3 |  | Architect defines the CSS variable structure; Developer implements it.
1.3 | Logo & Brand Element Replacement | Replace all our logos, product names, and favicons with SCCC's. |  |  | 2 |  | Pure development task.
1.4 | Typography & Layout Adjustment | Adjust font families, sizes, line heights, and weights to match SCCC's platform. |  |  | 2 |  | Pure development task.
1.5 | UI Component Fine-tuning & Testing | Perform visual regression testing on all components (forms, buttons, tables) and fix display issues caused by style changes. |  |  | 2 | 2
2 | Account Management (SSO) Integration |  | 2 | 3 | 9 | 2
2.1 | SSO Protocol & API Interface Analysis | Analyze SCCC's SSO technical documentation and understand the authentication flow. | 1 | 2 |  |  | Key Dependency: Requires clear, complete API docs and a test environment from the client.
2.2 | Backend Authentication Service Development | Modify the MaaS backend authentication module to integrate with SCCC's SSO. |  | 1 | 4 |  | Architect designs the core logic; Developer implements it.
2.3 | Frontend Login Flow Modification | Modify the MaaS login page to replace the standard form with a "Login with SCCC Account" button and handle the SSO redirection logic. |  |  | 5 |  | Pure development task.
2.4 | User Info Synchronization & Mapping | Create a corresponding user in the MaaS system upon first login and map user roles/permissions | 1 |  |  | 2 | PM confirms mapping rules with the client; QA validates the synchronization logic.
3 | Billing System Integration |  | 2 | 3 | 9 | 1
3.1 | Billing Model & API Interface Confirmation | (Prerequisite) Finalize the billing model (e.g., resource-based, not token-based) and obtain the billing system's API documentation. | 2 | 1 |  |  | Key Dependency: The project cannot proceed without a confirmed billing model.
3.2 | MaaS Resource Usage Monitoring Module | Develop a backend service to accurately track user resource consumption (instance start/stop times, GPU type, duration). |  | 2 | 4 |  | Architect designs a high-availability monitoring solution; Developer implements it.
3.3 | Billing Data Reporting Interface | Develop a service to periodically report resource usage data to the SCCC billing API in the required format, including retry and error handling logic. |  |  | 5 | 1 | Developer implements; QA validates interface robustness.
4 | Integration Testing & Deployment |  | 2 | 1 | 3 | 4
4.1 | End-to-End Integration Testing | Design and execute test cases covering the full workflow: SSO login -> create instance -> run -> destroy -> data reporting. |  |  |  | 3 | Led by QA; Developers assist with bug fixes.
4.2 | Deployment & Joint Debugging | Base on the MaaS Platform, deploy the models to the client's environment and configure all parameters for joint debugging with the SCCC platform. | 1 | 1 | 2 |  | PM coordinates; Architect provides technical support; Developer executes deployment.
4.3 | Technical Documentation | Prepare technical handover documents, including "SSO Integration Guide," "Billing Integration Guide," and "Deployment Manual." | 1 |  | 1 | 1 | PM handles project docs; Developer handles technical docs; QA handles test reports.
| Total |  | 9 | 10 | 30 | 9